## Instructions
Instructions |  |  | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name |  |  | 2225-swen-261-03-g-Team0
Testing Team Name |  |  | fill in when doing cross-team testing
PROJECT OVERVIEW |  |  | IN DEPTH ACCEPTANCE CRITERIA IN TEST PLAN SHEET
| SPRINT1 | SPRINT2 | SPRINT3
CREATE PRODUCT | PASSED
DELETE PRODUCT | PASSED
SEARCH PRODUCT | PASSED
EDIT PRODUCT | PASSED
CUSTOMER LOGIN |  | PASSED
CUSTOMER REGISTER |  | PASSED
ADMIN LOGIN |  | PASSED
ADD TO CART |  | PASSED
REMOVE FROM CART |  | PASSED
ACCESS CART |  | PASSED
CART PERSISTENCE |  | PASSED
DISCOUNT CODE |  | PASSED
SHIPPING FEATURE |  | PASSED
USER INTERFACE |  |  | PASSED
CHECKOUT |  |  | PASSED

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed) | Sprint 1 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. |  |  |  |  | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. |  |  |  |  | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. |  |  |  |  | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| Given that I am on the products page when there are products in the inventory then I see each product and short description. |  |  |  |  | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. |  |  |  |  | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
SPRINT2
| As a customer, I want to be able to add items to my shopping cart so that I can chose to buy an item. | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| As an Admin, I want to be able to add/delete items to the Inventory so that I can update the stock as intended. As an Admin I want to be able to change prices so that I can manage the inventory. | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| As an admin, I want to be able to log in to the e-store, so that I can access my account. As an admin, I want to be able to log out of the e-store so that I can leave my account | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| As a customer, I want to have a login so that I will be able to access the store and buy items. As a customer, I want to have a logout so that I will be to log out out of the store. | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| As a customer, I want to be able to delete items from the shopping cart so that I can change my mind about buying an item. | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| As a Customer, I should have the option of proceeding to payment either by Dining Dollars or Credit Card so as to complete my order | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| As a buyer/e-store owner, I want to be able to view the list of products . As a buyer/e-store owner, I want to be able to view the quantity of products available . As a buyer, I only want to be able to view the quantity of products available. As a e-store owner, I only want to be able to view and alter the quantity of products available. | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| As a buyer, I want to be able to search for a product using filters, so that I can easily find what I need. As an e-store owner, I want to be able to search for a product using filters, so that I can easily find what I need. | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| As a buyer, I want to be able to search for a product, so that I can easily find what I need. As an admin, I want to be able to search for a product, so that I can easily find what I need. | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| As a customer I want to be able to view the final cost of my shopping cart so I can keep track of the price of my current order. | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| As a customer, I want to have the option to save my shopping cart so that I can revisit a previous order. | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| As a customer I want to be able to view my shopping to cart so that I can ensure that I am buying the correct items. | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| GIVEN I enter a discount code WHEN prompted at checkout THEN the system should subtract the desired amount from the total and return a status code of 201 (VALID COUPON) | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| GIVEN I enter an invalid code WHEN prompted at checkout THEN the system should notify the user that the code was invalid and return a status code of 409 (INVALID COUPON) | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| GIVEN I select a shipping option WHEN when prompted at checkout THEN the system should accept the option and return a status code of 201 (SHIPPING PLAN UPDATED) | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| GIVEN I fail to select a shipping option WHEN prompted to select a shipping option THEN the system should return a message requesting the user to select a shipping option and return a status code of 409 (SHIPPING PLAN REQUIRED) | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| GIVEN I have an account with items in the shopping cart WHEN i may not be actively using the website THEN the system should keep those items and have a status code of 201 (CART SAVED) | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
| GIVEN I no longer am signed in WHEN I had a shopping cart with items THEN the cart should be cleared and a status code of 409 (CART EMPTIED) | Pass | Shimanto Bhowmik; 04/03/2023 ; all acceptance criteria passed
SPRINT 3
| As a User I would like to be able to add more than one of the same item to the cart . |  |  | Pass | Shimanto Bhowmik; 04/08/2023 ; all acceptance criteria passed
| Proper, professional, readable design documentation |  |  | Pass | Shimanto Bhowmik; 04/08/2023 ; all acceptance criteria passed
| As a User I would like to use a nice looking and easy to use webstore. As an Owner I would like to own a nice looking and easy to use webstore. |  |  | Pass | Shimanto Bhowmik; 04/08/2023 ; all acceptance criteria passed
| GIVEN I submit a payment option WHEN the option exists (is valid) THEN the system should accept the payment option and return a status code of 201 (CARD ACCEPTED) |  |  | Pass | Shimanto Bhowmik; 04/08/2023 ; all acceptance criteria passed
| GIVEN I submit a payment option WHEN the option doesn't exist (isn't valid) THEN the system should fail to accept the payment option and request again and return a status code of 409 (CARD DECLINED) |  |  | Pass | Shimanto Bhowmik; 04/08/2023 ; all acceptance criteria passed
| GIVEN an item has been purchased WHEN a product was bought from the customer, THEN the system should subtract an item from the inventory as desired and a status code of 201 (ITEM SUCCESSFULLY PURCHASED) |  |  | Pass | Shimanto Bhowmik; 04/08/2023 ; all acceptance criteria passed
| GIVEN an item doesn't exist WHEN it is purchased by the customer at checkout, THEN the system should decline the purchase and return a status code of 409 (INVALID ITEM) |  |  | Pass | Shimanto Bhowmik; 04/08/2023 ; all acceptance criteria passed